## Slide 1: 4/23/25 Status
MR Drilling
  5 of 8 DDW are Operational
  Pumps and Generators installed on 3 remaining wells
  Working on connecting to drainage system
J&O Well Drilling
  Completed 340’ Monitoring Well (Alta 9)
  Added Piezometer to existing Monitoring Well (Alta 8)
  Installed casing in DDW 8, next step development
Trouble shooting 3” East drainage line from WW22 to Ocean
  Using East Drainage nearly doubles ACLAD system capacity
Replacing ~3000’ of drainage line with 4” above ground line

## Slide 2: ACLAD Well Status 4.23.25
WW XX - Operating Wells
- existing drainage lines
- new drainage lines
- Operating DDW
  - Drilled and Finalizing
  - Proposed DDW
WW12
WW1
WW15
WW11
WW17
WW20
WW6
WW18
WW3
WW13
DDW24
DDW28
DDW27
DDW26
DDW16
DDW21
DDW25
DDW8
DDW22
DDW29
WW10
WW30
WW31
DDW27
Location | DDW Well | Status | GPM | Drainage
Thyme | 27 | Operating | ~50 | W
End of Sweetbay | 21 | Pump Installed | ~40 | E
End of Narcissa | 22 | Pump and Generator Installed | ~44 | E
Petak Sweetbay | 16 | Operating | 6 GPD | E
PBRC | 25 | Operating | 24 GPD | W
38 Narccissa | 24 | Operating | ~3 | W
Barth Sweetbay | 26 | Pump and Generator Installed | ~10 | W
Parks Cinnamon | 28 | Operating | 20 | E
Mid Sweetbay | 8 | Developing |  | W
Douglas Narcissa | 29 | Planned |  | E
 | Original Wells |  | K GPD | 
Narcissa and Ginger Root | WW 1 | Operating | 11 | W
Figtree | WW 3 | Needs Repair | 0 | W
CloveTree | WW6 | Operating | 6 | 
Figtree | WW10 | Operating | 3 | W
Bean Field | WW11 | Operating | 0 | E
Ginger Root | WW12 | Operating | 8 | W
Narcissa and Ginger Root | WW15 | Operating | 14 | E
Petak Sweetbay | WW16a | Operating | 6 | E
Thyme | WW17 | Replacing pump | 0 | W
Upper Cinnamon | WW 30 | Pump Installed | ~5 GPM @ 108’ | W
York | WW31 | Planned | ~ 180'x4" auger well | W
East Drainage
West Drainage