## Slide 1: ACLAD Status Dec 11, 2023
Fixed drain line in Well #2
City Wells
  Graded Olmstead Rd fissures
  Obtained permission to use Castle water
  Drilled well # 18
  Started drilling Well # 20
Started repairing PVDS Culvert
Participating in Landslide Meetings
  Cal Water: Tuesdays
  RPV Landslide Working Group
  LA Public Works for Altamira Canyon
Performing Water table measurements
  Purchased ENO Sounder
  Starting to install sounding tubes in wells
CURRENTLY PUMPING 169K GPD
  Spreadsheet Available on website
Water Testing
  PBCA resident volunteered to perform isotope testing to determine origin of water in wells
  Took samples during 11/15 rain storm
  Taking more samples and sending to the lab
Plans:
  Replace pumps in Well # 4
  Continue work on city wells and culvert and other landslide activities

## Slide 2: Drilling Started on PVDS Wells
Monday Unloading drill rig
Setting up on bluff
Drilling Well # 18
Well # 18 drilled to 176’
  Next Steps:
    Develop Well: Bail and wash out drilling mud
    Install electric, drain lines, and pump
Drill Wells 20, 19, and 9 in next 3 weeks
Friday: Installing 8” PVC
Casing
Sonic Mud Drilling Rig

## Slide 3: Cracks in PVDS Culvert
Multiple cracks in PVDS Culver
  Cracks range from 1” to 6” at pipe section joints
  11 large cracks to be repaired with expansion joints
PVDS Culvert Repair
  City council to authorize funding on Nov 14
  Repair work started 4 December
Developed design for expansion joint with rapid implementation
  Contractor on board
Reviewed by Hout Engineering
  Suggested adding new culver inside existing or fiberglass culvert insert
  Agreed that this could not be done prior to the rains
  Approved expansion design as a near term fix
Expansion Joint Design
Cracks at pipe joints
Most damage under
PVDS
Broken Security
Gate & hole at
exit

## Slide 4: Water Level Measurement
ACLAD measures water pumping weekly
  Pumping records back to 1992
  Traditionally has not measured water level on regular basis
Water Measurement program started 1/2023
  Measurement with Sonist water tape: difficult and time consuming
Recently purchase ENO sonic well sounder
  Installing sounding tubes in existing wells
  Installing permanent sounding tubes in new wells
Sonic Well Sounder
Well sounding tube
Water Level Tape