## Slide 1: ACLAD Status 2/10/2024 Pumping 80-100K GPD
Maintenance
  9 wells operational on generators, 8 wells sheared
  Multiple drainline breaks
  Planning to replace ~1600’ with above ground 4” PVC
Generator Noise Reduction
  PBCA Architectural Committee proposing guidelines
Surface Drainage highlights
  Narcissa/Cinnamon Phase 1 complete, add’l 80’ planned
  Vanderlip Dr. (Completed and repaired)
  Figtree Cul de Sac work started
ACLAD Trash Pump, a learning process
FEMA Appeal
  FEMA denied Winter Storms application due to “pre-existing landslide”
  RPV hiring appeal author for joint RPV/ACLAD/KCLAD Appeal – RPV asking for $5-10K contribution
View looking
Down WW 4
Attachments
  Detailed well status
  Surface Drainage planned Projects
  Deep Dewatering Well Plan
Pumping on Ginger Root
DRAFT

## Slide 2: Individual well status: 2/10/25 Current System Capacity ~100K GPD
WW | Location | GPD* | Comments
1 | Narcissa/Ginger Root | 13,642 | Operating on Generator
2 | Lower Narcissa |  | Sheared, pump stuck in casing, Will look into alternative pumps
3 | Figtree | 4,067 | Operating on Generator
4 | Lower Figtree |  | Sheared
6 | Clove Tree | 1,926 | Added propane shut off timer
7 | Mid Narcissa |  | Sheared
8 | Mid Sweetbay |  | Sheared
9 | Beach School |  | No Power, maybe able to power with DDW nearby.
10 | Figtree Cul de sac | 0 | No Water
11 | Bean Field | 29,877 | Operating on Generator
12 | Upper Ginger Root | 13,566 | Operating on Generator

## Slide 3: Individual well status 2/10/24
WW | Location | GPD* | Comments
13 | King/Sweetbay | 16,478 | Operating on Generator
15 | Vanderlip/Narcissa | 16,761 | Operating on Generator
16 | Petak/Sweetbay | 6,949 | Operating on Generator and shallow well pump
17 | Thyme | 0 | Working on sewer generator
18 | Olmsted |  | No Power
19 | Beach School |  | No Power, may be able to power with new DDW
20 | Olmsted |  | No Power
21 | Sweetbay/Yamaguchi |  | Sheared Planning to redrill
22 | End of Narcissa |  | Need to install generator
23 | Narcissa/Altamira |  | Sheared
24 | Narcissa/Hunter |  | Sheared

## Slide 4: Surface Drainage Projects

## Slide 5: ACLAD Well System with DDW
WW XX - Operating Wells
- existing drainage lines
- new drainage lines
- existing DDW
- new DDW
WW12
WW1
WW15
WW11
WW17
WW20
WW18
WW6
WW18
WW3
WW13
Keep existing high performing wells
  WW1, WW11, WW12, WW13, WW15
  Timed operation of WW3, WW6, WW17
Add 10 Deep Dewatering Wells
  Replace Sheared Wells (7)
  New locations (3)
Add 2 monitoring wells

## Slide 6: Deep Dewatering Wells

## Slide 7: Average DDW Expenses include:
Site Preparation
Well Drilling
Pump Installation
Drain Line (includes upsizing to existing lines where needed)
Generator Installation
Well and Generator enclosures
Propane Installation
Clean-up
Total $140-$200K per well