## Slide 1: ACLAD Status 9/9/2024
Maintenance
  10 wells operational on generators, 7 wells sheared, 5-11 wells need solar power, 2 wells need various repairs
  Installed 9 Generators
    Currently running on 5 gal tanks for ~ 6hrs per tank
    Working out fueling plan
  Repaired multiple system drain pipe breaks
Kelvin Canyon
  Spring draining down Vanderlip Dr.
  Re-assessing WW 15 drainage given lack of power
Surface Drainage
  Working with RPV on “Winterization Plan”
    Includes grading of Altamira Canyon fissures
  High priority projects:
    Narcissa/PBRC/Ginger Root
    Narcissa/Cinnamon
View looking
Down WW 4
Other Activities
  Pause in new wells till we define power plan
  RPV drilling 5 bore holes in ACL to assess Altamira slip surface
  Submitted final Damage Inventory to FEMA
Detailed well status follows
  Too soon to know pumping volume on propane generators

## Slide 2: Solar
Met with owner of Go Green Solar
Working on design for Solar/Battery power
Full time well uses ~36 solar panels + $20K battery
May need to change pumps to DC
WW | Location | Priority | On % | Comments
1 | Narcissa/Ginger Root | A | 100 | Possible Solar
2 | Lower Narcissa | 0 |  | Sheared
3 | Figtree | B | 10 | Generator or SCE
4 | Lower Figtree | 0 |  | Sheared
6 | Clove Tree | B | 10 | Possible Solar
7 | Mid Narcissa | 0 |  | Sheared
8 | Mid Sweetbay | B |  | Possible Solar or Generator near lift station
9 | Beach School | A | 50 | Possible Solar
10 | Figtree Cul de sac | A | 30 | Generator or SCE
11 | Bean Field | A | 100 | Solar or SCE (no generator because of access)
12 | Upper Ginger Root | A | 100 | Generator
13 | King/Sweetbay | A | 100 | Generator, Possible solar
15 | Vanderlip/Narcissa | A | 100 | Generator or SCE
16 | Petak/Sweetbay | A | 100 | Generator or SCE
17 | Thyme | B | 10 | Generator near lift station
18 | Olmsted | A | 50 | Possible Solar
19 | Beach School | A | 50 | Possible Solar
20 | Olmsted | A | 50 | Possible Solar
21 | Sweetbay/Yamaguchi | B |  | Possible Solar
22 | End of Narcissa | B | 20 | Possible Solar
23 | Narcissa/Altamira | 0 |  | Sheared Installing surface pump
24 | Narcissa/Hunter | A | 50 | Generator or SCE

## Slide 3: Individual well status: 7/2/24
WW | Location | GPD* | Comments
1 | Narcissa/Ginger Root | 16K | Generator Installed
2 | Lower Narcissa | 2K | Sheared, pump stuck in casing, Will look into alternative pumps
3 | Figtree | 1K | Generator Installed
4 | Lower Figtree |  | Sheared
6 | Clove Tree | 3K | Generator Installed, Need to remove plumbing from new well
7 | Mid Narcissa |  | Sheared
8 | Mid Sweetbay |  | Sheared
9 | Beach School | 4K | No Power
10 | Figtree Cul de sac | 3K | Generator Installed, Needs new meter
11 | Bean Field | 20-30K | No Power
12 | Upper Ginger Root | 10K | Generator Installed, Meter replaced
* Last month’s ~ave with SCE Power

## Slide 4: Individual well status
WW | Location | GPD* | Comments
13 | King/Sweetbay | 15K | Generator Installed
15 | Vanderlip/Narcissa | 13K | Generator Installed
16 | Petak/Sweetbay | 5-18K | Generator Installed Sheared, Water level 26’. Installed surface pump
17 | Thyme | 1K | Working on sewer generator, Replaced pump
18 | Olmsted | 4K | No Power
19 | Beach School | 4K | No Power
20 | Olmsted | 4K | No Power
21 | Sweetbay/Yamaguchi |  | Sheared Planning to redrill
22 | End of Narcissa |  | Need to investigate
23 | Narcissa/Altamira |  | Sheared Installing surface pump
24 | Narcissa/Hunter | 10K | Generator Installed
* Last month’s ~ave with SCE Power